## 1. Roster & Roles
Roles & Volunteer Roster |  |  |  |  | Camp Attendance Variables
[5 empty] | Dads | 16
[5 empty] | Daughters | 16
[5 empty] | Helpers / Leaders | 11
[5 empty] | Total Participants | 0
Role | Detailed Description & Default Duties | Assigned Leader | Contact Number | Email
Oversight Lead | • Ultimate decision-making authority during the camp. • Handles live issues (emergencies, weather changes). • Leads high-level reflections and debriefs. | Ian Sinclair | +27 63 893 9452 | sinclairian2408@gmail.com
Logistics Lead | • Manages all physical setup and breakdown. • Coordinates camp layout, tents/bivvies, fire preparation. | Neil Harrower | +27 71 950 8363 | neilharrower@gmail.com
Session Coordinator | • Facilitates the core structured spiritual/emotional sessions (e.g., Malachi discussion). | Marvin Welby-Solomon
Activity Facilitator | • Brings high energy to run the games and challenges (Clay Latte, Tug of War, Name Games). | Kingsley Williams | +27 83 260 5311
Catering / Fire Lead | • For the kick-off camp, both dinner and breakfast will be brought by the father and daughter. The key role here is to ensure the communal fires are started on time and maintained. | Kevin de Wet | +27 82 908 2460
Administration | • Handles all paperwork, nametags, and gate-keeping. | Paul Barter
Youth Track Leader 1 | • Supports youth-specific activities and engagement during free time.
Youth Track Leader 2 | • Supports youth-specific activities and engagement during free time.
General Helper 1 | Assists the Logistics and Catering leads where extra hands are needed. | Raldo Kruger | +27 84 511 8606
General Helper 2 | Assists the Activity Facilitator and Session Coordinator. | Gavin Graham
Communion Sub-Leader | • Sub-task role to specifically run and administer the communion elements on Sunday morning. | Richard Walker

## 2. Dynamic Timetable
Kickoff Camp Run Sheet
Change the Camp Start Time below. Live tasks will calculate sequentially. You can override any start time by typing over it.
| Camp Start Time: | 15:00
Day | Start Time | End Time | Duration (min) | Activity Name | Full Task Description | Linked Equipment | Assigned Role | Phase
Saturday | 0:00 | 0:00 | 30 | Arrival | Arrive at camp, name tags, get to know contacts | 0 | Administration | Arrival
Saturday | 0:00 | 0:00 | 30 | Ice Breaker | Get to know each other (Daughters introduce Fathers, name game) | 0 | Activity Facilitator | Ice Breaker
Saturday | 0:00 | 0:00 | 90 | Clay Latte | Father and daughter activities (Clay Latte) & Dam swim | 0 | Activity Facilitator | Activity
Saturday | 0:00 | 0:00 | 90 | Camp Setup | Set-up shelters, Bivvie equipment, prepare fire | 0 | Logistics Lead | Setup
Saturday | 0:00 | 0:00 | 60 | Dinner Prep | Ensure the fire is started on time and is ready with enough coals for families to cook. | 0 | Catering / Fire Lead | Dinner Prep
Saturday | 0:00 | 0:00 | 30 | Dinner | Dads and daughters cook and have supper together | 0 | Oversight Lead | Dinner
Saturday | 0:00 | 0:00 | 60 | Stokbrood | Marshmallows and stokbrood at fire, chat about questions | 0 | Session Coordinator | Evening
Saturday | 0:00 | 0:00 | 60 | Skits & Debrief | Present skits and carving, end of evening debrief | 0 | Oversight Lead | Wind Down
Saturday | 0:00 | 0:00 | 0 | Bed Time | Bed time | 0 | Oversight Lead | Lights Out
Sunday | 0:00 | 0:00 | 45 | Wake Up | Wake up, dam swim, boil kettles, coffee | 0 | Logistics Lead | Morning
Sunday | 0:00 | 0:00 | 90 | Malachi | Malachi discussion (sand demo) and communion | 0 | Session Coordinator | Session 1
Sunday | 0:00 | 0:00 | 30 | Communion | Administer Communion elements | 0 | Communion Sub-Leader | Communion
Sunday | 0:00 | 0:00 | 15 | Quiet Time | Father and Daughter Quiet time (reflect on Malachi) | 0 | Oversight Lead | Session 2
Sunday | 0:00 | 0:00 | 60 | Breakfast | Ensure fire is ready and boiling water is available. Families prepare and eat their own breakfast. | 0 | Catering / Fire Lead | Breakfast
Sunday | 0:00 | 0:00 | 60 | Manhood Talk | Dad's talk and daughters talk split | 0 | Session Coordinator | Session 3
Sunday | 0:00 | 0:00 | 15 | Final Debrief | Reflection on the sleepover, present carving | 0 | Oversight Lead | Debrief
Sunday | 0:00 | 0:00 | 60 | Pack Up | Pack up camp | 0 | Logistics Lead | Pack Up
Sunday | 0:00 | 0:00 | 45 | Tug of War | Father and Daughter Activity (Tug of war, Swim) | 0 | Activity Facilitator | Activity
Sunday | 0:00 | 0:00 | 0 | Departure | Depart from camp | 0 | Administration | Departure

## 3. Task Checklist
Pre-Camp Task Checklist
Action items and pre-planning organization that need to be completed before arrival.
Category | Task Description | Assigned Role | Status | Notes
Pre-Planning | Finalize RSVP list and dietary requirements | Administration | Not Started
Pre-Planning | Review medical forms | Oversight Lead | Not Started
Pre-Planning | Purchase all shopping list items (Communal items) | Catering / Fire Lead | Not Started
Pre-Planning | Print Name Tags and laminate Father/Daughter questions | Administration | Not Started
Pre-Planning | Confirm venue access codes and final layout | Logistics Lead | Not Started
Pre-Planning | Pack all camp equipment, tents, and activities gear | Logistics Lead | Not Started
Pre-Planning | Download YouTube Malachi scripture video | Session Coordinator | Not Started

## 4. Camp Equipment
General Camp Equipment List
Items required for general camp setup. These quantities do not typically change based on attendance.
Item | Qty | Assigned Role | Status | Notes
Washing bowl | 1 | Logistics Lead | To Buy
Dish towel | 2 | Logistics Lead | To Buy
Dish cloth | 5 | Logistics Lead | To Buy
Dish scourers | 5 | Logistics Lead | To Buy
Dish washing liquid | 1 | Logistics Lead | To Buy
Chopping board (wooden) | 4 | Catering / Fire Lead | To Buy
Garbage bags | 5 | Logistics Lead | To Buy
Spade | 1 | Logistics Lead | To Buy
Water Carrier | 1 | Logistics Lead | To Buy
Gas bottles | 2 | Logistics Lead | To Buy
Gas kettle (Large) | 1 | Logistics Lead | To Buy
Gas plate | 2 | Logistics Lead | To Buy
Gas kettle (small) | 1 | Logistics Lead | To Buy
Gas two plater | 1 | Logistics Lead | To Buy
Cutlery set | 1 | Catering / Fire Lead | To Buy
Gas fire starter (rod) | 1 | Logistics Lead | To Buy
First aid | 1 | Oversight Lead | To Buy
Tongs | 4 | Catering / Fire Lead | To Buy
Bodum | 1 | Catering / Fire Lead | To Buy
Braai grid (large) | 1 | Logistics Lead | To Buy
Journey Banner | 1 | Logistics Lead | To Buy
Fire lighter | 1 | Logistics Lead | To Buy
Camping mats | 6 | Logistics Lead | To Buy
Axe | 1 | Logistics Lead | To Buy
Mallet | 1 | Logistics Lead | To Buy

## 5. Activity Equipment
Activity Specific Equipment List
Quantities dynamically adjust based on Total Participants set in Tab 1.
Item | Base Formula | Calculated Qty | Linked Activity | Assigned Role | Status | Notes
Prop for earth shaking | Static | 1 | Malachi | Session Coordinator | To Buy
Speaker | Static | 1 | Malachi | Logistics Lead | To Buy
Projector | Static | 1 | Malachi | Logistics Lead | To Buy
Downloaded YouTube Malachi video | Static | 1 | Malachi | Session Coordinator | To Buy
Dad and daughter questions | 1 per pair | 0 | Stokbrood | Session Coordinator | To Buy
Stokbrood Stok | 1 per person | 0 | Stokbrood | Logistics Lead | To Buy
Tug of war rope | Static | 1 | Tug of War | Activity Facilitator | To Buy
Communion cups | 1 per person | 0 | Communion | Communion Sub-Leader | To Buy
Claylatt | 1 per person | 0 | Clay Latte | Activity Facilitator | To Buy
Clay - bag | Static | 1 | Clay Latte | Activity Facilitator | To Buy
Bivvy's (Shelter) | Total / 2 | 0 | Camp Setup | Logistics Lead | To Buy
Latte short (Shelter) | 1 per person | 0 | Camp Setup | Logistics Lead | To Buy
Latte long (Shelter) | 1 per person | 0 | Camp Setup | Logistics Lead | To Buy
Guy ropes (Shelter) | 2 per person | 0 | Camp Setup | Logistics Lead | To Buy
Pegs (Shelter) | 2 per person | 0 | Camp Setup | Logistics Lead | To Buy

## 6. Food Shopping
Communal Food & Catering Shopping List
Quantities dynamically adjust based on Total Participants set in Tab 1. Note: Fathers/Daughters bring their own dinner & breakfast foods.
Item | Calculated Qty needed | Assigned Role | Status | Notes
Dough for stokbrood | 0 | Catering / Fire Lead | To Buy
Coffee Instant | 0 | Catering / Fire Lead | To Buy
Coffee Ground | 0 | Catering / Fire Lead | To Buy
Long life milk | 0 | Catering / Fire Lead | To Buy
Sugar | 1kg | Catering / Fire Lead | To Buy
Rusks | 0 | Catering / Fire Lead | To Buy
Braai Brood (stok brood) | 0 | Catering / Fire Lead | To Buy
Marshmallows | 0 | Catering / Fire Lead | To Buy
Mieliemeal | 1kg | Catering / Fire Lead | To Buy
Rooibos | 1 box | Catering / Fire Lead | To Buy
Ceylon | 1 box | Catering / Fire Lead | To Buy
Hot chocolate | 0 | Catering / Fire Lead | To Buy
Marie biscuits | 0 | Catering / Fire Lead | To Buy
Tomato sauce | 2 bottles | Catering / Fire Lead | To Buy
Syrup | 1 x 500g | Catering / Fire Lead | To Buy
Communion juice (Grape) | 0 | Catering / Fire Lead | To Buy
Butro Butter | 500g | Catering / Fire Lead | To Buy
Communion loaf | 1 loaf | Catering / Fire Lead | To Buy

## 7. Activity Playbook
Activity Playbook
Detailed instructions and considerations for the lead running each activity.
Linked Activity | Goal / Objective | Instructions & Lead Considerations
Ice Breaker | Break the initial tension and get everyone laughing and connecting. | STEPS: 1. Have daughters introduce their fathers to the group (and vice versa). 2. Play a quick "Name Game" or "Two Truths and a Lie" (Camp Edition). LEAD CONSIDERATION: • Keep the energy high and fast-paced. • Don't let introductions drag on too long. • Ensure every single person feels seen and heard.
Clay Latte | Draw fathers and daughters together through teamwork and physical connection. | STEPS: 1. Tie the dad and daughter together at the ankles or wrists with a guy rope. 2. Set up an obstacle course or a challenge (e.g. crossing a line while carrying a cup of water, or building a clay structure). LEAD CONSIDERATION: • Emphasize that the goal isn't just winning, it's communicating and moving as one unit. • If frustration builds, pause and remind them to listen to each other.
Stokbrood | Quality, guided conversational time in a relaxed setting. | STEPS: 1. Layout tables, maize meal, dough, stokke (sticks), syrup, and marshmallows near the fire. 2. Ensure the printed question cards are handed out to each pair. 3. As they cook their stokbrood, fathers and daughters use the cards to spark deep conversations. LEAD CONSIDERATION: • Keep the fire well-stoked but safe. • Give families enough physical space around the fire to have private conversations. • Do not interrupt them once they are deep in conversation.
Skits & Debrief | Lighthearted fun followed by grounding the day's experiences. | STEPS: 1. Allow 10-15 minutes for groups to prepare a short, funny skit about something that happened today. 2. Follow up by presenting the carving (if applicable) and summarizing the key takeaways from Saturday. LEAD CONSIDERATION: • Set a supportive, cheering tone for the skits. • Transition smoothly from the loud fun of the skits into a calmer, more reflective tone for the debrief before bed.
Malachi | Spiritual reflection on restoration and the turning of hearts. | STEPS: 1. Show the downloaded YouTube video of the Malachi scripture (Malachi 4:6) using the projector and speaker. 2. Perform the Sand Demo: Use a tray with shaking sand to demonstrate how things naturally drift apart or settle, and discuss how intentional action (turning towards each other) is the solution. LEAD CONSIDERATION: • This is a visually and emotionally impactful session. • Ensure the tech (projector/speaker) is tested well beforehand. • Speak slowly and let the metaphor sink in.
Communion | Spiritual reflection, forgiveness, and partaking in the covenant together. | STEPS: 1. Provide the elements (grape juice and broken loaf) to each father/daughter pair. 2. Read Suggested Scriptures: 1 Corinthians 11:23-26 (The Lord's Supper) or Colossians 3:12-14 (Forgiveness and Love). 3. Guide the fathers to pray a blessing over their daughters before taking the elements. LEAD CONSIDERATION: • Create a quiet, reverent atmosphere. Allow ample time; do not rush this moment. • Have soft, instrumental worship music playing in the background if possible.
Quiet Time | Personal reflection on the Malachi session and Communion. | STEPS: 1. Fathers and daughters separate briefly, or sit quietly together without speaking, to reflect or journal. LEAD CONSIDERATION: • Clearly define the boundaries (e.g. "We will reconvene in 15 minutes at the main tent"). • Keep the camp entirely quiet during this block.
Manhood Talk | Equipping fathers for the journey ahead, while daughters have a separate empowering session. | STEPS: 1. Split the group: Dads in one area, daughters in another. 2. Lead a discussion with the dads about the weight and privilege of raising a daughter, drawing on the weekend's themes. LEAD CONSIDERATION: • Encourage vulnerability. • Ask open-ended questions like "What is your biggest fear in this season of her life?"
Tug of War | A final burst of fun, competitive teamwork before departing. | STEPS: 1. Set up the tug of war rope in a clear, flat area. 2. Run several heats: Dads vs. Dads, Daughters vs. Daughters, and then mixed teams. LEAD CONSIDERATION: • Safety first—ensure the ground isn't slippery and nobody wraps the rope around their hands/wrists. • Keep it highly competitive but lighthearted. End on a massive high note!