## 1. Roster & Roles
Roles & Volunteer Roster
Define the core roles and assign the primary volunteers to them.
Role | Detailed Description & Default Duties | Assigned Leader | Contact Number | Email
Oversight Lead | • Ultimate decision-making authority during the camp. • Handles live issues (emergencies, weather changes). • Leads high-level reflections and debriefs. • NOT responsible for physical setup or micromanaging tasks; focuses on the overall flow and safety. | Ian Sinclair | +27 63 893 9452 | sinclairian2408@gmail.com
Logistics Lead | • Manages all physical setup and breakdown. • Coordinates camp layout, tents/bivvies, fire preparation, and wood. • Ensures all physical camp equipment is transported, set up, and packed away safely. | Neil Harrower | +27 71 950 8363 | neilharrower@gmail.com
Session Coordinator | • Facilitates the core structured spiritual/emotional sessions (e.g., Malachi discussion, Communion). • Ensures questions are printed and ready for the Father/Daughter quality time. • Drives the theological and relational goals of the camp. | Marvin Welby-Solomon
Administration | • Handles all paperwork, nametags, and gate-keeping. • Checks people in upon arrival. • Tracks medical and dietary forms, and ensures all RSVPs match the attendees. | Paul Barter
Activity Facilitator | • Brings high energy to run the games and challenges (Clay Latte, Tug of War, Name Games). • Ensures equipment for games (ropes, clay, etc.) is ready and safe. • Briefs the group on the rules of the activities. | Kingsley Williams | +27 83 260 5311
Catering / Food Lead | • Owns the food schedule. Ensures meals are prepped on time. • Manages the "shopping list" items (coffee, milk, sugar, braai brood). • Coordinates the cleanup (washing bowls, dishwashing liquid). | Kevin de Wet | +27 82 908 2460
General Helper 1 | Assists the Logistics and Catering leads where extra hands are needed. | Raldo Kruger | +27 84 511 8606
General Helper 2 | Assists the Activity Facilitator and Session Coordinator. | Gavin Graham

## 2. Dynamic Timetable
Kickoff Camp Run Sheet (Including Pre-Planning)
Change the Camp Start Time below. Pre-camp tasks will calculate backwards based on their days offset. Live tasks will calculate sequentially.
| Camp Start Time: |  | 2026-01-31 15:00 | <-- Edit this cell to shift the entire timetable
Day | Phase | Offset (Days Before) | Duration (min) | Calculated Start | Calculated End | Activity / Task | Default Role | Custom Override | Final Leader
Pre-Camp | Planning | -14 | 60 | 0 | 0 | Finalize RSVP list and dietary requirements | Administration |  | 0
Pre-Camp | Planning | -7 | 60 | 0 | 0 | Review medical forms | Oversight Lead |  | 0
Pre-Camp | Prep | -5 | 120 | 0 | 0 | Purchase all shopping list items (Food/Drinks) | Catering / Food Lead |  | 0
Pre-Camp | Prep | -3 | 60 | 0 | 0 | Print Name Tags and laminate Father/Daughter questions | Administration |  | 0
Pre-Camp | Logistics | -2 | 60 | 0 | 0 | Confirm venue access codes and final layout | Logistics Lead |  | 0
Pre-Camp | Packing | -1 | 180 | 0 | 0 | Pack all camp equipment, tents, and activities gear | Logistics Lead |  | 0
Pre-Camp | Food Prep | -1 | 60 | 0 | 0 | Pre-pack braai brood and perishables | Catering / Food Lead |  | 0
Saturday | Travel | -0.125 | 90 | 0 | 0 | Drive to camp venue (3 hours before start) | Oversight Lead |  | 0
Saturday | Arrival | 0 | 30 | 0 | 0 | Arrive at camp, name tags, get to know contacts | Administration |  | 0
Saturday | Ice Breaker |  | 30 | 0 | 0 | Get to know each other (Daughters introduce Fathers, name game) | Activity Facilitator |  | 0
Saturday | Activity |  | 90 | 0 | 0 | Father and daughter activities (Clay Latte) & Dam swim | Activity Facilitator |  | 0
Saturday | Setup |  | 90 | 0 | 0 | Set-up shelters, Bivvie equipment, prepare fire | Logistics Lead |  | 0
Saturday | Dinner Prep |  | 60 | 0 | 0 | Prepare and Cook Supper | Catering / Food Lead |  | 0
Saturday | Dinner |  | 30 | 0 | 0 | Dads and daughters have supper together (quality time / questions) | Oversight Lead |  | 0
Saturday | Evening |  | 60 | 0 | 0 | Marshmallows and stokbrood at fire, chat about questions | Session Coordinator |  | 0
Saturday | Wind Down |  | 60 | 0 | 0 | Present skits and carving, end of evening debrief | Oversight Lead |  | 0
Saturday | Lights Out |  | 0 | 0 | 0 | Bed time | Oversight Lead |  | 0
Sunday | Morning |  | 45 | 0 | 0 | Wake up, dam swim, boil kettles, coffee | Logistics Lead |  | 0
Sunday | Session 1 |  | 90 | 0 | 0 | Malachi discussion (sand demo) and communion | Session Coordinator |  | 0
Sunday | Session 2 |  | 15 | 0 | 0 | Father and Daughter Quiet time (reflect on Malachi) | Oversight Lead |  | 0
Sunday | Breakfast |  | 60 | 0 | 0 | Breakfast | Catering / Food Lead |  | 0
Sunday | Session 3 |  | 60 | 0 | 0 | Dad's talk and daughters talk split | Session Coordinator |  | 0
Sunday | Debrief |  | 15 | 0 | 0 | Reflection on the sleepover, present carving | Oversight Lead |  | 0
Sunday | Pack Up |  | 60 | 0 | 0 | Pack up camp | Logistics Lead |  | 0
Sunday | Activity |  | 45 | 0 | 0 | Father and Daughter Activity (Tug of war, Swim) | Activity Facilitator |  | 0
Sunday | Departure |  | 0 | 0 | 0 | Depart from camp | Administration |  | 0
Formulas:
Calculated Start = IF(ISNUMBER([Offset (Days Before)]), D4 + [Offset (Days Before)], D4)
Calculated Start = IF(ISNUMBER([Offset (Days Before)]), D4 + [Offset (Days Before)], [Calculated End, row above])
Calculated End = [Calculated Start] + ([Duration (min)]/1440)

## 3. Task Checklist
General Task Checklist
Action items that do not relate to physical equipment.
Category | Task Description | Default Role | Custom Override | Final Assigned | Status
Administration | Finalize RSVP list and dietary requirements | Administration |  | 0 | Not Started
Administration | Print Name Tags | Administration |  | 0 | Not Started
Safety | Review medical forms | Oversight Lead |  | 0 | Not Started
Activities | Laminate Father/Daughter questions | Session Coordinator |  | 0 | Not Started
Logistics | Confirm venue booking and access code | Logistics Lead |  | 0 | Not Started
Food | Purchase all shopping list items | Catering / Food Lead |  | 0 | Not Started
Food | Pre-pack braai brood | Catering / Food Lead |  | 0 | Not Started

## 4. Equipment & Shopping
Master Equipment & Shopping List
All physical items grouped by category.
Category | Item | Qty | Default Role | Custom Override | Final Assigned | Status
Camp Equipment | Washing bowl | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Dish towel | 2 | Logistics Lead |  | 0 | Pending
Camp Equipment | Dish cloth | 5 | Logistics Lead |  | 0 | Pending
Camp Equipment | Dish scourers | 5 | Logistics Lead |  | 0 | Pending
Camp Equipment | Dish washing liquid | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Chopping board (wooden) | 4 | Catering / Food Lead |  | 0 | Pending
Camp Equipment | Garbage bags | 5 | Logistics Lead |  | 0 | Pending
Camp Equipment | Spade | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Water Carrier | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Gas bottles | 2 | Logistics Lead |  | 0 | Pending
Camp Equipment | Gas kettle (Large) | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Gas plate | 2 | Logistics Lead |  | 0 | Pending
Camp Equipment | Gas kettle (small) | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Gas two plater | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Cutlery set | 1 | Catering / Food Lead |  | 0 | Pending
Camp Equipment | Gas fire starter (rod) | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | First aid | 1 | Oversight Lead |  | 0 | Pending
Camp Equipment | Tongs | 4 | Catering / Food Lead |  | 0 | Pending
Camp Equipment | Bodum | 1 | Catering / Food Lead |  | 0 | Pending
Camp Equipment | Braai grid (large) | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Journey Banner | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Fire lighter | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Camping mats | 6 | Logistics Lead |  | 0 | Pending
Camp Equipment | Axe | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Mallet | 1 | Logistics Lead |  | 0 | Pending
Camp Equipment | Prop for earth shaking | 1 | Session Coordinator |  | 0 | Pending
Activities | Dad and daughter questions | 16 | Session Coordinator |  | 0 | Pending
Activities | Stokbrood Stok | 43 | Logistics Lead |  | 0 | Pending
Activities | Tug of war rope | 1 | Activity Facilitator |  | 0 | Pending
Activities | Communion cups | 50 | Session Coordinator |  | 0 | Pending
Activities | Claylatt | 43 | Activity Facilitator |  | 0 | Pending
Activities | Clay - bag | 1 | Activity Facilitator |  | 0 | Pending
Activities | Bivvy's (Shelter) | 21.5 | Logistics Lead |  | 0 | Pending
Activities | Latte short (Shelter) | 43 | Logistics Lead |  | 0 | Pending
Activities | Latte long (Shelter) | 43 | Logistics Lead |  | 0 | Pending
Activities | Guy ropes (Shelter) | 86 | Logistics Lead |  | 0 | Pending
Activities | Pegs (Shelter) | 86 | Logistics Lead |  | 0 | Pending
Shopping List (Food) | Coffee Instant | 2 jars | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Coffee Ground | 1 Kg | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Long life milk | 12L | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Sugar | 1kg | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Rusks | 8 boxes | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Braai Brood (stok brood) | 6 bags | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Marshmallows | 3 x 300g | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Mieliemeal | 1kg | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Rooibos | 1 box | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Ceylon | 1 box | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Hot chocolate | 1 x 500g | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Marie biscuits | 4 pkts | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Tomato sauce | 2 bottles | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Syrup | 1 x 500g | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Communion juice (Grape) | 2 L | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Butro Butter | 500g | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Communion loaf | 1 loaf | Catering / Food Lead |  | 0 | Pending
Personal Equipment (Bring) | Plates & Bowls | 1/person | Administration |  | 0 | Pending
Personal Equipment (Bring) | Coffee mug & Water bottle | 1/person | Administration |  | 0 | Pending
Personal Equipment (Bring) | Loo paper | 1 roll | Administration |  | 0 | Pending
Personal Equipment (Bring) | Tent, Chairs, Mattress | 1/family | Administration |  | 0 | Pending
Personal Equipment (Bring) | Sleeping bags, Pillows | 1/person | Administration |  | 0 | Pending
Personal Equipment (Bring) | Towels, Jackets, Swim stuff | 1/person | Administration |  | 0 | Pending
Personal Equipment (Bring) | Toiletries, Meds, Suncream | 1/person | Administration |  | 0 | Pending
Personal Equipment (Bring) | Torches/batteries | 1/person | Administration |  | 0 | Pending
Personal Equipment (Bring) | Insect repellent | 1/person | Administration |  | 0 | Pending