## 1. Roster & Roles
Roles & Volunteer Roster
Role | Detailed Description & Default Duties | Assigned Leader | Contact Number | Email
Oversight Lead | • Ultimate decision-making authority during the camp. • Handles live issues (emergencies, weather changes). • Leads high-level reflections and debriefs. | Ian Sinclair | +27 63 893 9452 | sinclairian2408@gmail.com
Logistics Lead | • Manages all physical setup and breakdown. • Coordinates camp layout, tents/bivvies, fire preparation. | Neil Harrower | +27 71 950 8363 | neilharrower@gmail.com
Session Coordinator | • Facilitates the core structured spiritual/emotional sessions (e.g., Malachi discussion). | Marvin Welby-Solomon
Communion Leader | • Specifically runs the communion session on Sunday morning. | Richard Walker
Administration | • Handles all paperwork, nametags, and gate-keeping. | Paul Barter
Activity Facilitator | • Brings high energy to run the games and challenges (Clay Latte, Tug of War, Name Games). | Kingsley Williams | +27 83 260 5311
Catering / Food Lead | • Owns the food schedule. Ensures meals are prepped on time. | Kevin de Wet | +27 82 908 2460
General Helper 1 | Assists the Logistics and Catering leads where extra hands are needed. | Raldo Kruger | +27 84 511 8606
General Helper 2 | Assists the Activity Facilitator and Session Coordinator. | Gavin Graham

## 2. Dynamic Timetable
Kickoff Camp Run Sheet
Change the Camp Start Time below. Live tasks will calculate sequentially. Type into "Manual Start Override" to break the chain and set a custom time.
| Camp Start Time: |  | 2026-01-31 15:00
Day | Phase | Manual Start Override | Calculated Start | Calculated End | Duration (min) | Activity Name | Full Task Description | Linked Equipment | Default Role | Custom Override | Final Leader
Saturday | Arrival |  | 0 | 0 | 30 | Arrival | Arrive at camp, name tags, get to know contacts | 0 | Administration |  | 0
Saturday | Ice Breaker |  | 0 | 0 | 30 | Ice Breaker | Get to know each other (Daughters introduce Fathers, name game) | 0 | Activity Facilitator |  | 0
Saturday | Activity |  | 0 | 0 | 90 | Clay Latte | Father and daughter activities (Clay Latte) & Dam swim | 0 | Activity Facilitator |  | 0
Saturday | Setup |  | 0 | 0 | 90 | Camp Setup | Set-up shelters, Bivvie equipment, prepare fire | 0 | Logistics Lead |  | 0
Saturday | Dinner Prep |  | 0 | 0 | 60 | Dinner Prep | Prepare and Cook Supper | 0 | Catering / Food Lead |  | 0
Saturday | Dinner |  | 0 | 0 | 30 | Dinner | Dads and daughters have supper together | 0 | Oversight Lead |  | 0
Saturday | Evening |  | 0 | 0 | 60 | Stokbrood | Marshmallows and stokbrood at fire, chat about questions | 0 | Session Coordinator |  | 0
Saturday | Wind Down |  | 0 | 0 | 60 | Skits & Debrief | Present skits and carving, end of evening debrief | 0 | Oversight Lead |  | 0
Saturday | Lights Out |  | 0 | 0 | 0 | Bed Time | Bed time | 0 | Oversight Lead |  | 0
Sunday | Morning |  | 0 | 0 | 45 | Wake Up | Wake up, dam swim, boil kettles, coffee | 0 | Logistics Lead |  | 0
Sunday | Session 1 |  | 0 | 0 | 90 | Malachi | Malachi discussion (sand demo) and communion | 0 | Session Coordinator |  | 0
Sunday | Communion |  | 0 | 0 | 30 | Communion | Administer Communion elements | 0 | Communion Leader |  | 0
Sunday | Session 2 |  | 0 | 0 | 15 | Quiet Time | Father and Daughter Quiet time (reflect on Malachi) | 0 | Oversight Lead |  | 0
Sunday | Breakfast |  | 0 | 0 | 60 | Breakfast | Breakfast | 0 | Catering / Food Lead |  | 0
Sunday | Session 3 |  | 0 | 0 | 60 | Manhood Talk | Dad's talk and daughters talk split | 0 | Session Coordinator |  | 0
Sunday | Debrief |  | 0 | 0 | 15 | Final Debrief | Reflection on the sleepover, present carving | 0 | Oversight Lead |  | 0
Sunday | Pack Up |  | 0 | 0 | 60 | Pack Up | Pack up camp | 0 | Logistics Lead |  | 0
Sunday | Activity |  | 0 | 0 | 45 | Tug of War | Father and Daughter Activity (Tug of war, Swim) | 0 | Activity Facilitator |  | 0
Sunday | Departure |  | 0 | 0 | 0 | Departure | Depart from camp | 0 | Administration |  | 0
Formulas:
Calculated Start = IF([Manual Start Override]<>"", [Manual Start Override], D4)
Calculated Start = IF([Manual Start Override]<>"", [Manual Start Override], [Calculated End, row above])
Calculated End = [Calculated Start] + ([Duration (min)]/1440)

## 3. Task Checklist
Pre-Camp Task Checklist
Action items and pre-planning organization that need to be completed before arrival.
Category | Task Description | Default Role | Custom Override | Final Assigned | Status
Pre-Planning | Finalize RSVP list and dietary requirements | Administration |  | 0 | Not Started
Pre-Planning | Review medical forms | Oversight Lead |  | 0 | Not Started
Pre-Planning | Purchase all shopping list items (Food/Drinks) | Catering / Food Lead |  | 0 | Not Started
Pre-Planning | Print Name Tags and laminate Father/Daughter questions | Administration |  | 0 | Not Started
Pre-Planning | Confirm venue access codes and final layout | Logistics Lead |  | 0 | Not Started
Pre-Planning | Pack all camp equipment, tents, and activities gear | Logistics Lead |  | 0 | Not Started
Pre-Planning | Pre-pack braai brood and perishables | Catering / Food Lead |  | 0 | Not Started
Pre-Planning | Download YouTube Malachi scripture video | Session Coordinator |  | 0 | Not Started

## 4. Equipment & Shopping
Master Equipment & Shopping List
Category | Item | Qty | Linked Activity | Default Role | Custom Override | Final Assigned | Status
Camp Equipment | Washing bowl | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Dish towel | 2 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Dish cloth | 5 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Dish scourers | 5 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Dish washing liquid | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Chopping board (wooden) | 4 |  | Catering / Food Lead |  | 0 | Pending
Camp Equipment | Garbage bags | 5 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Spade | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Water Carrier | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Gas bottles | 2 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Gas kettle (Large) | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Gas plate | 2 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Gas kettle (small) | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Gas two plater | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Cutlery set | 1 |  | Catering / Food Lead |  | 0 | Pending
Camp Equipment | Gas fire starter (rod) | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | First aid | 1 |  | Oversight Lead |  | 0 | Pending
Camp Equipment | Tongs | 4 |  | Catering / Food Lead |  | 0 | Pending
Camp Equipment | Bodum | 1 |  | Catering / Food Lead |  | 0 | Pending
Camp Equipment | Braai grid (large) | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Journey Banner | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Fire lighter | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Camping mats | 6 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Axe | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Mallet | 1 |  | Logistics Lead |  | 0 | Pending
Camp Equipment | Prop for earth shaking | 1 | Malachi | Session Coordinator |  | 0 | Pending
Camp Equipment | Speaker | 1 | Malachi | Logistics Lead |  | 0 | Pending
Camp Equipment | Projector | 1 | Malachi | Logistics Lead |  | 0 | Pending
Activities | Downloaded YouTube Malachi video | 1 | Malachi | Session Coordinator |  | 0 | Pending
Activities | Dad and daughter questions | 16 | Stokbrood | Session Coordinator |  | 0 | Pending
Activities | Stokbrood Stok | 43 | Stokbrood | Logistics Lead |  | 0 | Pending
Activities | Tug of war rope | 1 | Tug of War | Activity Facilitator |  | 0 | Pending
Activities | Communion cups | 50 | Communion | Communion Leader |  | 0 | Pending
Activities | Claylatt | 43 | Clay Latte | Activity Facilitator |  | 0 | Pending
Activities | Clay - bag | 1 | Clay Latte | Activity Facilitator |  | 0 | Pending
Activities | Bivvy's (Shelter) | 21.5 | Camp Setup | Logistics Lead |  | 0 | Pending
Activities | Latte short (Shelter) | 43 | Camp Setup | Logistics Lead |  | 0 | Pending
Activities | Latte long (Shelter) | 43 | Camp Setup | Logistics Lead |  | 0 | Pending
Activities | Guy ropes (Shelter) | 86 | Camp Setup | Logistics Lead |  | 0 | Pending
Activities | Pegs (Shelter) | 86 | Camp Setup | Logistics Lead |  | 0 | Pending
Shopping List (Food) | Dough for stokbrood | 43 portions | Stokbrood | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Coffee Instant | 2 jars | Wake Up | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Coffee Ground | 1 Kg | Wake Up | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Long life milk | 12L |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Sugar | 1kg |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Rusks | 8 boxes |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Braai Brood (stok brood) | 6 bags | Stokbrood | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Marshmallows | 3 x 300g | Stokbrood | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Mieliemeal | 1kg |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Rooibos | 1 box |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Ceylon | 1 box |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Hot chocolate | 1 x 500g |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Marie biscuits | 4 pkts |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Tomato sauce | 2 bottles |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Syrup | 1 x 500g |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Communion juice (Grape) | 2 L | Communion | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Butro Butter | 500g |  | Catering / Food Lead |  | 0 | Pending
Shopping List (Food) | Communion loaf | 1 loaf | Communion | Catering / Food Lead |  | 0 | Pending
Personal Equipment (Bring) | Plates & Bowls | 1/person |  | Administration |  | 0 | Pending
Personal Equipment (Bring) | Coffee mug & Water bottle | 1/person |  | Administration |  | 0 | Pending
Personal Equipment (Bring) | Loo paper | 1 roll |  | Administration |  | 0 | Pending
Personal Equipment (Bring) | Tent, Chairs, Mattress | 1/family |  | Administration |  | 0 | Pending
Personal Equipment (Bring) | Sleeping bags, Pillows | 1/person |  | Administration |  | 0 | Pending
Personal Equipment (Bring) | Towels, Jackets, Swim stuff | 1/person |  | Administration |  | 0 | Pending
Personal Equipment (Bring) | Toiletries, Meds, Suncream | 1/person |  | Administration |  | 0 | Pending
Personal Equipment (Bring) | Torches/batteries | 1/person |  | Administration |  | 0 | Pending
Personal Equipment (Bring) | Insect repellent | 1/person |  | Administration |  | 0 | Pending

## 5. Activity Playbook
Activity Playbook
Detailed rules, concepts, and instructions for each activity.
Linked Activity | Goal / Objective | Instructions & Rules
Clay Latte | Draw fathers and daughters together through teamwork. | Dad and daughter tied together with a guy rope. Must navigate an obstacle course or complete a challenge as a mixed team across the middle line.
Stokbrood | Quality conversational time. | Layout tables, maize meal, dough, stokke, syrup, and marshmallows by the fire. Dads and daughters cook their stokbrood while discussing the printed question cards.
Malachi | Spiritual reflection on restoration. | Show the downloaded YouTube video of the Malachi scripture on the projector/speaker. Demo the shaking sand in a tray. Discuss how the solution is Fathers turning towards children and vice versa.
Communion | Spiritual reflection and partaking. | Administer the communion elements (juice and loaf) together.
Pack Up | Teamwork and responsibility. | Sons/Daughters oversee the packing of their family tent and gear before participating in the final activity.