## 1. Roster & Roles
Roles & Volunteer Roster
Role | Detailed Description & Default Duties | Assigned Leader | Contact Number | Email
Oversight Lead | • Ultimate decision-making authority during the camp. • Handles live issues (emergencies, weather changes). • Leads high-level reflections and debriefs. | Ian Sinclair | +27 63 893 9452 | sinclairian2408@gmail.com
Logistics Lead | • Manages all physical setup and breakdown. • Coordinates camp layout, tents/bivvies, fire preparation. | Neil Harrower | +27 71 950 8363 | neilharrower@gmail.com
Session Coordinator | • Facilitates the core structured spiritual/emotional sessions (e.g., Malachi discussion). | Marvin Welby-Solomon
Communion Leader | • Specifically runs the communion session on Sunday morning. | Richard Walker
Administration | • Handles all paperwork, nametags, and gate-keeping. | Paul Barter
Activity Facilitator | • Brings high energy to run the games and challenges (Clay Latte, Tug of War, Name Games). | Kingsley Williams | +27 83 260 5311
Catering / Food Lead | • Owns the food schedule. Ensures meals are prepped on time. | Kevin de Wet | +27 82 908 2460
General Helper 1 | Assists the Logistics and Catering leads where extra hands are needed. | Raldo Kruger | +27 84 511 8606
General Helper 2 | Assists the Activity Facilitator and Session Coordinator. | Gavin Graham

## 2. Dynamic Timetable
Kickoff Camp Run Sheet
Change the Camp Start Time below. Live tasks will calculate sequentially. Type into "Manual Start Override" to set a custom time.
| Camp Start Time: | 15:00
Day | Manual Start Override | Calculated Start | Calculated End | Duration (min) | Activity Name | Full Task Description | Linked Equipment | Default Role | Change Ownership | Final Leader | Phase
Saturday |  | 0:00 | 0:00 | 30 | Arrival | Arrive at camp, name tags, get to know contacts | 0 | Administration |  | 0 | Arrival
Saturday |  | 0:00 | 0:00 | 30 | Ice Breaker | Get to know each other (Daughters introduce Fathers, name game) | 0 | Activity Facilitator |  | 0 | Ice Breaker
Saturday |  | 0:00 | 0:00 | 90 | Clay Latte | Father and daughter activities (Clay Latte) & Dam swim | 0 | Activity Facilitator |  | 0 | Activity
Saturday |  | 0:00 | 0:00 | 90 | Camp Setup | Set-up shelters, Bivvie equipment, prepare fire | 0 | Logistics Lead |  | 0 | Setup
Saturday |  | 0:00 | 0:00 | 60 | Dinner Prep | Prepare and Cook Supper | 0 | Catering / Food Lead |  | 0 | Dinner Prep
Saturday |  | 0:00 | 0:00 | 30 | Dinner | Dads and daughters have supper together | 0 | Oversight Lead |  | 0 | Dinner
Saturday |  | 0:00 | 0:00 | 60 | Stokbrood | Marshmallows and stokbrood at fire, chat about questions | 0 | Session Coordinator |  | 0 | Evening
Saturday |  | 0:00 | 0:00 | 60 | Skits & Debrief | Present skits and carving, end of evening debrief | 0 | Oversight Lead |  | 0 | Wind Down
Saturday |  | 0:00 | 0:00 | 0 | Bed Time | Bed time | 0 | Oversight Lead |  | 0 | Lights Out
Sunday |  | 0:00 | 0:00 | 45 | Wake Up | Wake up, dam swim, boil kettles, coffee | 0 | Logistics Lead |  | 0 | Morning
Sunday |  | 0:00 | 0:00 | 90 | Malachi | Malachi discussion (sand demo) and communion | 0 | Session Coordinator |  | 0 | Session 1
Sunday |  | 0:00 | 0:00 | 30 | Communion | Administer Communion elements | 0 | Communion Leader |  | 0 | Communion
Sunday |  | 0:00 | 0:00 | 15 | Quiet Time | Father and Daughter Quiet time (reflect on Malachi) | 0 | Oversight Lead |  | 0 | Session 2
Sunday |  | 0:00 | 0:00 | 60 | Breakfast | Breakfast | 0 | Catering / Food Lead |  | 0 | Breakfast
Sunday |  | 0:00 | 0:00 | 60 | Manhood Talk | Dad's talk and daughters talk split | 0 | Session Coordinator |  | 0 | Session 3
Sunday |  | 0:00 | 0:00 | 15 | Final Debrief | Reflection on the sleepover, present carving | 0 | Oversight Lead |  | 0 | Debrief
Sunday |  | 0:00 | 0:00 | 60 | Pack Up | Pack up camp | 0 | Logistics Lead |  | 0 | Pack Up
Sunday |  | 0:00 | 0:00 | 45 | Tug of War | Father and Daughter Activity (Tug of war, Swim) | 0 | Activity Facilitator |  | 0 | Activity
Sunday |  | 0:00 | 0:00 | 0 | Departure | Depart from camp | 0 | Administration |  | 0 | Departure

## 3. Task Checklist
Pre-Camp Task Checklist
Action items and pre-planning organization that need to be completed before arrival.
Category | Task Description | Default Role | Change Ownership | Final Assigned | Status
Pre-Planning | Finalize RSVP list and dietary requirements | Administration |  | 0 | Not Started
Pre-Planning | Review medical forms | Oversight Lead |  | 0 | Not Started
Pre-Planning | Purchase all shopping list items (Food/Drinks) | Catering / Food Lead |  | 0 | Not Started
Pre-Planning | Print Name Tags and laminate Father/Daughter questions | Administration |  | 0 | Not Started
Pre-Planning | Confirm venue access codes and final layout | Logistics Lead |  | 0 | Not Started
Pre-Planning | Pack all camp equipment, tents, and activities gear | Logistics Lead |  | 0 | Not Started
Pre-Planning | Pre-pack braai brood and perishables | Catering / Food Lead |  | 0 | Not Started
Pre-Planning | Download YouTube Malachi scripture video | Session Coordinator |  | 0 | Not Started

## 4. Camp Equipment
General Camp Equipment List
Items required for general camp setup. These are not tied to specific activities.
Item | Qty | Default Role | Change Ownership | Final Assigned | Status
Washing bowl | 1 | Logistics Lead |  | 0 | Pending
Dish towel | 2 | Logistics Lead |  | 0 | Pending
Dish cloth | 5 | Logistics Lead |  | 0 | Pending
Dish scourers | 5 | Logistics Lead |  | 0 | Pending
Dish washing liquid | 1 | Logistics Lead |  | 0 | Pending
Chopping board (wooden) | 4 | Catering / Food Lead |  | 0 | Pending
Garbage bags | 5 | Logistics Lead |  | 0 | Pending
Spade | 1 | Logistics Lead |  | 0 | Pending
Water Carrier | 1 | Logistics Lead |  | 0 | Pending
Gas bottles | 2 | Logistics Lead |  | 0 | Pending
Gas kettle (Large) | 1 | Logistics Lead |  | 0 | Pending
Gas plate | 2 | Logistics Lead |  | 0 | Pending
Gas kettle (small) | 1 | Logistics Lead |  | 0 | Pending
Gas two plater | 1 | Logistics Lead |  | 0 | Pending
Cutlery set | 1 | Catering / Food Lead |  | 0 | Pending
Gas fire starter (rod) | 1 | Logistics Lead |  | 0 | Pending
First aid | 1 | Oversight Lead |  | 0 | Pending
Tongs | 4 | Catering / Food Lead |  | 0 | Pending
Bodum | 1 | Catering / Food Lead |  | 0 | Pending
Braai grid (large) | 1 | Logistics Lead |  | 0 | Pending
Journey Banner | 1 | Logistics Lead |  | 0 | Pending
Fire lighter | 1 | Logistics Lead |  | 0 | Pending
Camping mats | 6 | Logistics Lead |  | 0 | Pending
Axe | 1 | Logistics Lead |  | 0 | Pending
Mallet | 1 | Logistics Lead |  | 0 | Pending

## 5. Activity Equipment
Activity Specific Equipment List
Equipment strictly tied to specific timetable activities.
Item | Qty | Linked Activity | Default Role | Change Ownership | Final Assigned | Status
Prop for earth shaking | 1 | Malachi | Session Coordinator |  | 0 | Pending
Speaker | 1 | Malachi | Logistics Lead |  | 0 | Pending
Projector | 1 | Malachi | Logistics Lead |  | 0 | Pending
Downloaded YouTube Malachi video | 1 | Malachi | Session Coordinator |  | 0 | Pending
Dad and daughter questions | 16 | Stokbrood | Session Coordinator |  | 0 | Pending
Stokbrood Stok | 43 | Stokbrood | Logistics Lead |  | 0 | Pending
Tug of war rope | 1 | Tug of War | Activity Facilitator |  | 0 | Pending
Communion cups | 50 | Communion | Communion Leader |  | 0 | Pending
Claylatt | 43 | Clay Latte | Activity Facilitator |  | 0 | Pending
Clay - bag | 1 | Clay Latte | Activity Facilitator |  | 0 | Pending
Bivvy's (Shelter) | 21.5 | Camp Setup | Logistics Lead |  | 0 | Pending
Latte short (Shelter) | 43 | Camp Setup | Logistics Lead |  | 0 | Pending
Latte long (Shelter) | 43 | Camp Setup | Logistics Lead |  | 0 | Pending
Guy ropes (Shelter) | 86 | Camp Setup | Logistics Lead |  | 0 | Pending
Pegs (Shelter) | 86 | Camp Setup | Logistics Lead |  | 0 | Pending

## 6. Food Shopping
Food & Catering Shopping List
Item | Qty | Default Role | Change Ownership | Final Assigned | Status
Dough for stokbrood | 43 portions | Catering / Food Lead |  | 0 | Pending
Coffee Instant | 2 jars | Catering / Food Lead |  | 0 | Pending
Coffee Ground | 1 Kg | Catering / Food Lead |  | 0 | Pending
Long life milk | 12L | Catering / Food Lead |  | 0 | Pending
Sugar | 1kg | Catering / Food Lead |  | 0 | Pending
Rusks | 8 boxes | Catering / Food Lead |  | 0 | Pending
Braai Brood (stok brood) | 6 bags | Catering / Food Lead |  | 0 | Pending
Marshmallows | 3 x 300g | Catering / Food Lead |  | 0 | Pending
Mieliemeal | 1kg | Catering / Food Lead |  | 0 | Pending
Rooibos | 1 box | Catering / Food Lead |  | 0 | Pending
Ceylon | 1 box | Catering / Food Lead |  | 0 | Pending
Hot chocolate | 1 x 500g | Catering / Food Lead |  | 0 | Pending
Marie biscuits | 4 pkts | Catering / Food Lead |  | 0 | Pending
Tomato sauce | 2 bottles | Catering / Food Lead |  | 0 | Pending
Syrup | 1 x 500g | Catering / Food Lead |  | 0 | Pending
Communion juice (Grape) | 2 L | Catering / Food Lead |  | 0 | Pending
Butro Butter | 500g | Catering / Food Lead |  | 0 | Pending
Communion loaf | 1 loaf | Catering / Food Lead |  | 0 | Pending

## 7. Activity Playbook
Activity Playbook
Detailed rules, concepts, and instructions for each activity.
Linked Activity | Goal / Objective | Instructions & Rules
Clay Latte | Draw fathers and daughters together through teamwork. | Dad and daughter tied together with a guy rope. Must navigate an obstacle course or complete a challenge as a mixed team across the middle line.
Stokbrood | Quality conversational time. | Layout tables, maize meal, dough, stokke, syrup, and marshmallows by the fire. Dads and daughters cook their stokbrood while discussing the printed question cards.
Malachi | Spiritual reflection on restoration. | Show the downloaded YouTube video of the Malachi scripture on the projector/speaker. Demo the shaking sand in a tray. Discuss how the solution is Fathers turning towards children and vice versa.
Communion | Spiritual reflection and partaking. | Administer the communion elements (juice and loaf) together.
Pack Up | Teamwork and responsibility. | Sons/Daughters oversee the packing of their family tent and gear before participating in the final activity.