## 1. Roster & Roles
Roles & Volunteer Roster
Role | Detailed Description & Default Duties | Assigned Leader | Contact Number | Email
Oversight Lead | • Ultimate decision-making authority during the camp. • Handles live issues (emergencies, weather changes). • Leads high-level reflections and debriefs. | Ian Sinclair | +27 63 893 9452 | sinclairian2408@gmail.com
Logistics Lead | • Manages all physical setup and breakdown. • Coordinates camp layout, tents/bivvies, fire preparation. | Neil Harrower | +27 71 950 8363 | neilharrower@gmail.com
Session Coordinator | • Facilitates the core structured spiritual/emotional sessions (e.g., Malachi discussion). | Marvin Welby-Solomon
Communion Leader | • Specifically runs the communion session on Sunday morning. | Richard Walker
Administration | • Handles all paperwork, nametags, and gate-keeping. | Paul Barter
Activity Facilitator | • Brings high energy to run the games and challenges (Clay Latte, Tug of War, Name Games). | Kingsley Williams | +27 83 260 5311
Catering / Food Lead | • Owns the food schedule. Ensures meals are prepped on time. | Kevin de Wet | +27 82 908 2460
General Helper 1 | Assists the Logistics and Catering leads where extra hands are needed. | Raldo Kruger | +27 84 511 8606
General Helper 2 | Assists the Activity Facilitator and Session Coordinator. | Gavin Graham

## 2. Dynamic Timetable
Kickoff Camp Run Sheet
Change the Camp Start Time below. Live tasks will calculate sequentially. Type into "Manual Start Override" to set a custom time.
| Camp Start Time: | 15:00
Day | Manual Start Override | Calculated Start | Calculated End | Duration (min) | Activity Name | Full Task Description | Linked Equipment | Default Role | Change Ownership | Final Leader | Phase
Saturday |  | 0:00 | 0:00 | 30 | Arrival | Arrive at camp, name tags, get to know contacts | 0 | Administration |  | 0 | Arrival
Saturday |  | 0:00 | 0:00 | 30 | Ice Breaker | Get to know each other (Daughters introduce Fathers, name game) | 0 | Activity Facilitator |  | 0 | Ice Breaker
Saturday |  | 0:00 | 0:00 | 90 | Clay Latte | Father and daughter activities (Clay Latte) & Dam swim | 0 | Activity Facilitator |  | 0 | Activity
Saturday |  | 0:00 | 0:00 | 90 | Camp Setup | Set-up shelters, Bivvie equipment, prepare fire | 0 | Logistics Lead |  | 0 | Setup
Saturday |  | 0:00 | 0:00 | 60 | Dinner Prep | Prepare and Cook Supper | 0 | Catering / Food Lead |  | 0 | Dinner Prep
Saturday |  | 0:00 | 0:00 | 30 | Dinner | Dads and daughters have supper together | 0 | Oversight Lead |  | 0 | Dinner
Saturday |  | 0:00 | 0:00 | 60 | Stokbrood | Marshmallows and stokbrood at fire, chat about questions | 0 | Session Coordinator |  | 0 | Evening
Saturday |  | 0:00 | 0:00 | 60 | Skits & Debrief | Present skits and carving, end of evening debrief | 0 | Oversight Lead |  | 0 | Wind Down
Saturday |  | 0:00 | 0:00 | 0 | Bed Time | Bed time | 0 | Oversight Lead |  | 0 | Lights Out
Sunday |  | 0:00 | 0:00 | 45 | Wake Up | Wake up, dam swim, boil kettles, coffee | 0 | Logistics Lead |  | 0 | Morning
Sunday |  | 0:00 | 0:00 | 90 | Malachi | Malachi discussion (sand demo) and communion | 0 | Session Coordinator |  | 0 | Session 1
Sunday |  | 0:00 | 0:00 | 30 | Communion | Administer Communion elements | 0 | Communion Leader |  | 0 | Communion
Sunday |  | 0:00 | 0:00 | 15 | Quiet Time | Father and Daughter Quiet time (reflect on Malachi) | 0 | Oversight Lead |  | 0 | Session 2
Sunday |  | 0:00 | 0:00 | 60 | Breakfast | Breakfast | 0 | Catering / Food Lead |  | 0 | Breakfast
Sunday |  | 0:00 | 0:00 | 60 | Manhood Talk | Dad's talk and daughters talk split | 0 | Session Coordinator |  | 0 | Session 3
Sunday |  | 0:00 | 0:00 | 15 | Final Debrief | Reflection on the sleepover, present carving | 0 | Oversight Lead |  | 0 | Debrief
Sunday |  | 0:00 | 0:00 | 60 | Pack Up | Pack up camp | 0 | Logistics Lead |  | 0 | Pack Up
Sunday |  | 0:00 | 0:00 | 45 | Tug of War | Father and Daughter Activity (Tug of war, Swim) | 0 | Activity Facilitator |  | 0 | Activity
Sunday |  | 0:00 | 0:00 | 0 | Departure | Depart from camp | 0 | Administration |  | 0 | Departure

## 3. Task Checklist
Pre-Camp Task Checklist
Action items and pre-planning organization that need to be completed before arrival.
Category | Task Description | Default Role | Change Ownership | Final Assigned | Status
Pre-Planning | Finalize RSVP list and dietary requirements | Administration |  | 0 | Not Started
Pre-Planning | Review medical forms | Oversight Lead |  | 0 | Not Started
Pre-Planning | Purchase all shopping list items (Food/Drinks) | Catering / Food Lead |  | 0 | Not Started
Pre-Planning | Print Name Tags and laminate Father/Daughter questions | Administration |  | 0 | Not Started
Pre-Planning | Confirm venue access codes and final layout | Logistics Lead |  | 0 | Not Started
Pre-Planning | Pack all camp equipment, tents, and activities gear | Logistics Lead |  | 0 | Not Started
Pre-Planning | Pre-pack braai brood and perishables | Catering / Food Lead |  | 0 | Not Started
Pre-Planning | Download YouTube Malachi scripture video | Session Coordinator |  | 0 | Not Started

## 4. Camp Equipment
General Camp Equipment List
Items required for general camp setup. These are not tied to specific activities.
Item | Qty | Default Role | Change Ownership | Final Assigned | Status
Washing bowl | 1 | Logistics Lead |  | 0 | Pending
Dish towel | 2 | Logistics Lead |  | 0 | Pending
Dish cloth | 5 | Logistics Lead |  | 0 | Pending
Dish scourers | 5 | Logistics Lead |  | 0 | Pending
Dish washing liquid | 1 | Logistics Lead |  | 0 | Pending
Chopping board (wooden) | 4 | Catering / Food Lead |  | 0 | Pending
Garbage bags | 5 | Logistics Lead |  | 0 | Pending
Spade | 1 | Logistics Lead |  | 0 | Pending
Water Carrier | 1 | Logistics Lead |  | 0 | Pending
Gas bottles | 2 | Logistics Lead |  | 0 | Pending
Gas kettle (Large) | 1 | Logistics Lead |  | 0 | Pending
Gas plate | 2 | Logistics Lead |  | 0 | Pending
Gas kettle (small) | 1 | Logistics Lead |  | 0 | Pending
Gas two plater | 1 | Logistics Lead |  | 0 | Pending
Cutlery set | 1 | Catering / Food Lead |  | 0 | Pending
Gas fire starter (rod) | 1 | Logistics Lead |  | 0 | Pending
First aid | 1 | Oversight Lead |  | 0 | Pending
Tongs | 4 | Catering / Food Lead |  | 0 | Pending
Bodum | 1 | Catering / Food Lead |  | 0 | Pending
Braai grid (large) | 1 | Logistics Lead |  | 0 | Pending
Journey Banner | 1 | Logistics Lead |  | 0 | Pending
Fire lighter | 1 | Logistics Lead |  | 0 | Pending
Camping mats | 6 | Logistics Lead |  | 0 | Pending
Axe | 1 | Logistics Lead |  | 0 | Pending
Mallet | 1 | Logistics Lead |  | 0 | Pending

## 5. Activity Equipment
Activity Specific Equipment List
Equipment strictly tied to specific timetable activities.
Item | Qty | Linked Activity | Default Role | Change Ownership | Final Assigned | Status
Prop for earth shaking | 1 | Malachi | Session Coordinator |  | 0 | Pending
Speaker | 1 | Malachi | Logistics Lead |  | 0 | Pending
Projector | 1 | Malachi | Logistics Lead |  | 0 | Pending
Downloaded YouTube Malachi video | 1 | Malachi | Session Coordinator |  | 0 | Pending
Dad and daughter questions | 16 | Stokbrood | Session Coordinator |  | 0 | Pending
Stokbrood Stok | 43 | Stokbrood | Logistics Lead |  | 0 | Pending
Tug of war rope | 1 | Tug of War | Activity Facilitator |  | 0 | Pending
Communion cups | 50 | Communion | Communion Leader |  | 0 | Pending
Claylatt | 43 | Clay Latte | Activity Facilitator |  | 0 | Pending
Clay - bag | 1 | Clay Latte | Activity Facilitator |  | 0 | Pending
Bivvy's (Shelter) | 21.5 | Camp Setup | Logistics Lead |  | 0 | Pending
Latte short (Shelter) | 43 | Camp Setup | Logistics Lead |  | 0 | Pending
Latte long (Shelter) | 43 | Camp Setup | Logistics Lead |  | 0 | Pending
Guy ropes (Shelter) | 86 | Camp Setup | Logistics Lead |  | 0 | Pending
Pegs (Shelter) | 86 | Camp Setup | Logistics Lead |  | 0 | Pending

## 6. Food Shopping
Food & Catering Shopping List
Item | Qty | Default Role | Change Ownership | Final Assigned | Status
Dough for stokbrood | 43 portions | Catering / Food Lead |  | 0 | Pending
Coffee Instant | 2 jars | Catering / Food Lead |  | 0 | Pending
Coffee Ground | 1 Kg | Catering / Food Lead |  | 0 | Pending
Long life milk | 12L | Catering / Food Lead |  | 0 | Pending
Sugar | 1kg | Catering / Food Lead |  | 0 | Pending
Rusks | 8 boxes | Catering / Food Lead |  | 0 | Pending
Braai Brood (stok brood) | 6 bags | Catering / Food Lead |  | 0 | Pending
Marshmallows | 3 x 300g | Catering / Food Lead |  | 0 | Pending
Mieliemeal | 1kg | Catering / Food Lead |  | 0 | Pending
Rooibos | 1 box | Catering / Food Lead |  | 0 | Pending
Ceylon | 1 box | Catering / Food Lead |  | 0 | Pending
Hot chocolate | 1 x 500g | Catering / Food Lead |  | 0 | Pending
Marie biscuits | 4 pkts | Catering / Food Lead |  | 0 | Pending
Tomato sauce | 2 bottles | Catering / Food Lead |  | 0 | Pending
Syrup | 1 x 500g | Catering / Food Lead |  | 0 | Pending
Communion juice (Grape) | 2 L | Catering / Food Lead |  | 0 | Pending
Butro Butter | 500g | Catering / Food Lead |  | 0 | Pending
Communion loaf | 1 loaf | Catering / Food Lead |  | 0 | Pending

## 7. Activity Playbook
Activity Playbook
Detailed instructions and considerations for the lead running each activity.
Linked Activity | Goal / Objective | Instructions & Lead Considerations
Ice Breaker | Break the initial tension and get everyone laughing and connecting. | STEPS: 1. Have daughters introduce their fathers to the group (and vice versa). 2. Play a quick "Name Game" or "Two Truths and a Lie" (Camp Edition). LEAD CONSIDERATION: • Keep the energy high and fast-paced. • Don't let introductions drag on too long. • Ensure every single person feels seen and heard.
Clay Latte | Draw fathers and daughters together through teamwork and physical connection. | STEPS: 1. Tie the dad and daughter together at the ankles or wrists with a guy rope. 2. Set up an obstacle course or a challenge (e.g. crossing a line while carrying a cup of water, or building a clay structure). LEAD CONSIDERATION: • Emphasize that the goal isn't just winning, it's communicating and moving as one unit. • If frustration builds, pause and remind them to listen to each other.
Stokbrood | Quality, guided conversational time in a relaxed setting. | STEPS: 1. Layout tables, maize meal, dough, stokke (sticks), syrup, and marshmallows near the fire. 2. Ensure the printed question cards are handed out to each pair. 3. As they cook their stokbrood, fathers and daughters use the cards to spark deep conversations. LEAD CONSIDERATION: • Keep the fire well-stoked but safe. • Give families enough physical space around the fire to have private conversations. • Do not interrupt them once they are deep in conversation.
Skits & Debrief | Lighthearted fun followed by grounding the day's experiences. | STEPS: 1. Allow 10-15 minutes for groups to prepare a short, funny skit about something that happened today. 2. Follow up by presenting the carving (if applicable) and summarizing the key takeaways from Saturday. LEAD CONSIDERATION: • Set a supportive, cheering tone for the skits. • Transition smoothly from the loud fun of the skits into a calmer, more reflective tone for the debrief before bed.
Malachi | Spiritual reflection on restoration and the turning of hearts. | STEPS: 1. Show the downloaded YouTube video of the Malachi scripture (Malachi 4:6) using the projector and speaker. 2. Perform the Sand Demo: Use a tray with shaking sand to demonstrate how things naturally drift apart or settle, and discuss how intentional action (turning towards each other) is the solution. LEAD CONSIDERATION: • This is a visually and emotionally impactful session. • Ensure the tech (projector/speaker) is tested well beforehand. • Speak slowly and let the metaphor sink in.
Communion | Spiritual reflection, forgiveness, and partaking in the covenant together. | STEPS: 1. Provide the elements (grape juice and broken loaf) to each father/daughter pair. 2. Read Suggested Scriptures: 1 Corinthians 11:23-26 (The Lord's Supper) or Colossians 3:12-14 (Forgiveness and Love). 3. Guide the fathers to pray a blessing over their daughters before taking the elements. LEAD CONSIDERATION: • Create a quiet, reverent atmosphere. Allow ample time; do not rush this moment. • Have soft, instrumental worship music playing in the background if possible.
Quiet Time | Personal reflection on the Malachi session and Communion. | STEPS: 1. Fathers and daughters separate briefly, or sit quietly together without speaking, to reflect or journal. LEAD CONSIDERATION: • Clearly define the boundaries (e.g. "We will reconvene in 15 minutes at the main tent"). • Keep the camp entirely quiet during this block.
Manhood Talk | Equipping fathers for the journey ahead, while daughters have a separate empowering session. | STEPS: 1. Split the group: Dads in one area, daughters in another. 2. Lead a discussion with the dads about the weight and privilege of raising a daughter, drawing on the weekend's themes. LEAD CONSIDERATION: • Encourage vulnerability. • Ask open-ended questions like "What is your biggest fear in this season of her life?"
Tug of War | A final burst of fun, competitive teamwork before departing. | STEPS: 1. Set up the tug of war rope in a clear, flat area. 2. Run several heats: Dads vs. Dads, Daughters vs. Daughters, and then mixed teams. LEAD CONSIDERATION: • Safety first—ensure the ground isn't slippery and nobody wraps the rope around their hands/wrists. • Keep it highly competitive but lighthearted. End on a massive high note!